## start-from-scratch
Things to fix from sprint 2 |  |  |  |  | Working on it | Finished
Task | Status | Person | Start Date | Finish Date
upscale textures resolution for tiles + make them smaller | Finished | Ting | 2022-02-27 | 2022-03-01
Adjust tile in game size | Finished | Ting | 2022-02-27 | 2022-03-01
Clean up sprites for projectiles [black bars + some src rects too small] | Finished | Craig | 2022-02-28 | 2022-03-02
Boomerang needs to return to the player's current position |  | Craig
Make the old man smaller in game | Finished | Zening | 2022-03-02 | 2022-03-04
Clean up sprites for enemies [blackbars + backgrounds + src rects contain other frames] | Finished | Zening | 2022-03-03 | 2022-03-05
upscale textures resolution for items | Finished | Austin | 2022-03-04 | 2022-03-06
Fairy item needs to move around |  | Austin
Collision checking : Luke Wingert
Name | Status | Person | Start Date | Finish Date
Implement IBoxCollider in player | Finished | Luke | 2022-02-26 | 2022-02-26
Implement Sort and Sweep | Finished | Luke | 2022-02-26 | 2022-03-08
flesh out the test level more | Finished | Luke | 2022-03-07 | 2022-03-08
Use console logs to test | Finished | Luke | 2022-03-07 | 2022-03-08
Separate draw and update in player | Finished | Luke | 2022-02-26 | 2022-02-26
Dispatch correct collision handlers | Finished | Luke | 2022-03-07 | 2022-03-08
Collision handling : Zening + Craig
Task | Status | Person | Start Date | Finish Date
Implement the IBoxCollider Interface in enemies | Finished | Luke | 2022-03-05 | 2022-03-07
Implement the IBoxCollider Interface in Projectiles | Finished | Luke | 2022-03-05 | 2022-03-07
player - enemy - handler | Finished | Luke | 2022-03-05 | 2022-03-07
player - block - handler | Finished | Luke | 2022-03-05 | 2022-03-07
player - tile - handler [might need to split this one up] | Finished | Luke | 2022-03-05 | 2022-03-07
player - enemyProjectile - handler | Finished | Zening | 2022-03-05 | 2022-03-07
player - item - handler | Finished | Luke | 2022-03-05 | 2022-03-07
enemy - block - handler | Finished | Zening | 2022-03-05 | 2022-03-07
enemy - boundary - handler | Finished | Zening | 2022-03-05 | 2022-03-07
enemy - pushableBlock - handler | Finished | Zening | 2022-03-05 | 2022-03-07
enemy - friendlyProjectile - handler | Finished | Luke | 2022-03-05 | 2022-03-07
Level Design [Ting] + Level Loading [Austin]
Task | Status | Person | Start Date | Finish Date
Implement IBoxCollider in items | Finished | Austin | 2022-02-28 | 2022-03-01
Implement IBoxCollider in tiles | Finished | Ting | 2022-02-28 | 2022-03-01
Create 10~ levels in csv files | Finished | Ting | 2022-02-28 | 2022-03-01
Encapsulate level loading in a class seperate from game | Finished | Austin | 2022-03-01 | 2022-03-04
Generate levels given a csv input | Finished | Austin | 2022-03-01 | 2022-03-04
Room Walls Class | Finished | Ting | 2022-02-28 | 2022-02-28
Door Classes | Finished | Austin | 2022-03-01 | 2022-03-04
Bug Fixing in Level Loading/Designing | Finished | Ting | 2022-03-10 | 2022-03-11